## 2019 WMP
*Note that the scope of the programs included in the 2019 WMP is different from the 2020 WMP; thus, the total population of programs is smaller than what we have submitted in the 2020 and the 2021 WMP filings
2019 WMP Filing - Initial Forecasts (A) | [5 empty] | 2019 Actuals (C)
2019 WMP Section | 2020 WMP Approximate Equivalent Section | Program/Strategy | Mapped Programs | Estimated | Estimated Annual Cost: | $ Thousands
|  |  |  | Annual Cost: | 2019 Expense (1,000s) | Capital Actual | Expense Actual
|  |  |  | 2019 Capital (1,000s) |  | 2019 | 2019
4 |  | Wildfire Safety Strategy and Programs
4 | 5.3.10.5-1 | PMO | PMO | 500 | 8000 | 9.8397 | 31183.5031
4.1 |  | Operational Practices
4.1.1 | N/A | Recloser Operations | Reclose Blocking (Manual) | - | - | 0 | 0
4.1.2 | 5.3.6.3 | Personnel Work Procedures in Conditions of Elevated Fire Risk | N/A | - | - | NA | NA
4.1.3 | 5.3.6.2 | Safety and Infrastructure Protection Teams | Safety and Infrastructure Protection Team | 6200 | 12300 | 642.3525 | 12918.2641
4.1.4 | 5.3.9.7 | Aviation Resources | Aviation Resources | 2100 | 2400 | 3725.7933 | 6620.3561
4.2 |  | Wildfire Safety Inspection Programs
4.2.1 | 5.3.4.9 | WSIP, Distribution | Distribution Inspection / Repair | $220,000-$620,000 | $130,000-$200,000 | 231288.7724 | 277613.4983
4.2.2 | 5.3.4.10 | WSIP, Transmission | Transmission Inspection / Repair | $282,000-$402,000 | $162,000-$167,000 | 255414.1552 | 519127.8804
4.2.3 | 5.3.4.15-2 | WSIP, Substation | Distribution Substation Inspection / Repair |  | $1,000-$2,000 | 9476.6161 | 13486.1391
| 5.3.4.15-1 |  | Transmission Substation Inspection/Repair | – | $1,000-$2,000 | 1234.7655 | 2823.101
4.3 |  | System Hardening
4.3.1 | 5.3.3.17-1 | Pole Material | Wildfire System Hardening | 236900 | – | 281083.8799 | 0
4.3.2 | N/A | Pole Loading and Replacement (Transmission) | Light Duty Steel Poles for Transmission | 500 | - | 0 | 0
4.3.2 | N/A | Pole Loading and Replacement (Distribution) | Wildfire System Hardening | Part of System Hardening | – | See System Hardening Above | 0
4.3.3 | 5.3.3.3 | Conductor | Wildfire System Hardening | Part of System Hardening | – | See System Hardening Above | 0
4.3.4 | 5.3.3.9-1 | System Protection | Automation and Protection (SCADA) | 15600 | 300 | 6815.689 | 201.1531
4.3.5 | 5.3.3.17-2 | Equipment | Non‐exempt Surge Arrester Replacement Program | 71600 | – | 21767.3505 | 0
4.4 |  | Enhanced Vegetation Management
4.4.1 | 5.3.5 | Vegetation Trimming and Overhanging Tree Limbs | Enhanced Vegetation Management | – | 338300 | 0 | 470426.0941
4.4.2 | 5.3.5 | High Fire-Threat District VM Inspection Strategy
4.4.3 | 5.3.5 | Inspecting Trees with a Potential Strike Path to Power Lines
4.4.4 | 5.3.5 | At-risk Species Management
4.4.5 | 5.3.5 | Challenges Associated With Enhanced Vegetation Management
4.4.6 | 5.3.5 | Community and Environmental Impacts
Other | 5.3.5 | CEMA Costs | CEMA – Drought Tree Mortality | – | 85900 | 0 | 85143.7349
Other | 5.3.5.18-2 | Substation Vegetation Management | Sub Veg Mgt (T)- identified in WSIP | – | $2,000 - $4,000 | 0 | 1259.3591
| 5.3.5.18-1 |  | Sub Veg Mgt (D)- identified in WSIP | – | $4,000 - $5,000 | 0 | 7277.5774
4.5 |  | Enhanced Situational Awareness
4.5.1 | 5.3.2 | Meteorological Operations and Advanced Situational Awareness | See Programs Below | See Programs Below | See Programs Below | See Programs Below | See Programs Below
4.5.2 | 5.3.2.4 | Fire Spread Modeling | See 4.5.5 | – | – | See "Advanced Fire Modeling" | See "Advanced Fire Modeling"
4.5.3 | 5.3.2.1-1 | Weather Stations | Expanded Weather Station Deployment | 8200 | 300 | 6933.6763 | 605.6784
4.5.4 | 5.3.2.1-2 | Camera Deployment Strategy | Wildfire Cameras | – | 4600 | 0 | 2063.3694
4.5.5 | 5.3.2.1-3 | Satellite Fire Detection Systems | Satellite Fire Detection System | – | 400 | 0 | 0
4.5.6 | 5.3.2.6 | Storm Outage Prediction Model (SOPP) | SOPP Model Automation | – | 200 | 0 | 0
4.5.7 | 5.3.2.7-1 | Wildfire Safety Operations Center | Wildfire Safety Operations Center | 700 | 15900 | 2120.9695 | 5678.2011
Other | 5.3.2.4 | Advanced Fire Modeling | Advanced Fire Modeling | – | 1600 | 0 | 4133.6125
4.6 |  | Public Safety Power Safety Shutoff
4.6.1 | 5.3.6.5-1 | PSPS Decision Factors | Public Safety Power Shutoff | – | 16500 | 756.8257 | 219885.9709
4.6.2 | 5.3.6.5-1 | Strategies to Enhance PSPS Efficiency While Reducing Associated Impacts
4.6.3 | 5.3.6.5-1 | PSPS Notification Strategies
4.6.4 | 5.3.6.5-1 | Re-energization strategy
4.6.2.1 | 5.3.3.8-1 | Impact Mitigation through System Sectionalizing | Granular Sectionalizing | 5200 | – | 51193.1082 | 0
4.6.2.2 | 5.3.3.8-3 | Resilience Zones | Resilience Zones | 10600 | – | 3319.9938 | 0
4.6.2.3 | 5.3.9.3 | Customer Services and Programs | N/A - Costs and program scope are still being finalized | – | – | See PSPS Above | See PSPS Above
4.7 |  | Alternative Technologies
4.7.1 | 5.3.3.17-3 | Rapid Earth Fault Current Limiter Pilot Project | Rapid Earth Current Fault Limiter | – | 7000 | 0 | 1835.4004
4.7.2 | 5.3.2.2-1 | Enhanced Wires Down Detection Project | Enhanced Wire Down Detection | 2100 | 200 | 390.5367 | 0.17818
4.7.3 | Multiple | Other Alternative Technologies | N/A | – | – | NA | NA
4.8 |  | Post Incident Recovery, Restoration and Remediation
4.8.1 | 5.3.9 | Post-Incident Recovery | N/A | – | – | NA | NA
4.8.2 | 5.3.9 | Restoration | N/A | – | – | NA | NA
4.8.3 | 5.3.9 | Remediation | N/A | – | – | NA | NA
Other |  | Support
Other | 5.3.7.5 | IT Costs | N/A | $16,000 - $33,000 | $13,000 - $18,000 | 16134.9541 | 5581.4293

## 2020 WMP
|  |  | 2020 Comparison - Forecast vs Actuals |  |  |  | 2021 - 2022 WMP Forecasts
2020 WMP Initiatives |  |  | Expense $Thousands |  | Capital $ Thousands |  | Expense $Thousands |  | Capital $ Thousands
Section | Initiative number | Initiative name | 2020 Actuals | 2020 Forecast | 2020 Actuals | 2020 Forecast | 2021 Fcst | 2022 Fcst | 2021 Fcst | 2022 Fcst
Table 21 5.3.1 Risk assessment and mapping | 5.3.1.1 | 5.3.1.1, A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | 634.6424 | 609.1135 | 0 | 0 | 624.3414 | 639.9499 | 0 | 0
Table 21 5.3.1 Risk assessment and mapping | 5.3.1.2 | 5.3.1.2, Climate-driven risk map and modelling based on various relevant weather scenarios | 955.836 | 770 | 0 | 0 | 1373 | 1322 | 0 | 0
Table 21 5.3.1 Risk assessment and mapping | 5.3.1.3 | 5.3.1.3, Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 634.6424 | 609.1135 | 0 | 0 | 624.3414 | 639.9499 | 0 | 0
Table 21 5.3.1 Risk assessment and mapping | 5.3.1.4 | 5.3.1.4, Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 15.5357 | 23.1064 | 0 | 0 | 23.6841 | 24.2762 | 0 | 0
Table 21 5.3.1 Risk assessment and mapping | 5.3.1.5 | 5.3.1.5, Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 3584 | 3300 | 0 | 0 | 3382.5 | 3467.0625 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.1-1 | 5.3.2.1-1, Advanced weather monitoring and weather stations, Weather Station | 111.2093 | 559 | 8314.9397 | 8077.8609 | 576.888 | 595.3484 | 5717.5632 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.1-2 | 5.3.2.1-2, Advanced weather monitoring and weather stations, Cameras | 6955.7637 | 3508.8 | 0 | 0 | 3621 | 1083.7126 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.1-3 | 5.3.2.1-3, Advanced weather monitoring and weather stations, Satellite Fire Detection | 257 | 341.592 | 0 | 0 | 352.515 | 363.8021 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.2-1 | 5.3.2.2-1, Continuous monitoring sensors, Enhanced Wires Down | 3.6572 | 212.78 | 1215.5724 | 716.8 | 212.78 | 212.78 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.2-2 | 5.3.2.2-2, Continuous monitoring sensors, EPIC - DFA and EDF, FZA | 750.2566 | 1126.467 | 0 | 0 | 0 | 0 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.2-3 | 5.3.2.2-3, Continuous monitoring sensors, Line Sensor Devices | 0 | 0 | 2590.165 | 3918.6715 | 0 | 0 | 6600.6927 | 7379.6284
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.2-4 | 5.3.2.2-4, Continuous monitoring sensors, Arc Fault Signature Library | 563.4847 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.2-5 | 5.3.2.2-5, Continuous monitoring sensors, Transmission SEL0T400L Relays | 0 | 0 | 633 | 700 | 0 | 0 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.2-6 | 5.3.2.2-6, Continuous monitoring sensors, Sensor IQ | 1870.7814 | 1819.2733 | 0 | 0 | 86.5851 | 95.6883 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.3 | 5.3.2.3, Fault indicators for detecting faults on electric lines and equipment | 1470 | 3040 | 0 | 0 | 3800 | 4600 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.4 | 5.3.2.4, Forecast of a fire risk index, fire potential index, or similar, Advance Fire Modeling | 5712.0503 | 1822.848 | 0 | 0 | 1986.66 | 2155.9324 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.5 | 5.3.2.5, Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 3068.3805 | 4733.5331 | 0 | 0 | 7411.3036 | 8257.1755 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.6 | 5.3.2.6, Weather forecasting and estimating impacts on electric lines and equipment, SOPP | 1627.0829 | 1974.216 | 0 | 0 | 2037.345 | 2102.5783 | 0 | 0
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.7-1 | 5.3.2.7-1, Other, Wildife Safety Operations Center (WSOC) | 4117.327 | 9189.7378 | -34.0887 | 51.2 | 11355.8858 | 12171.7792 | 52.38 | 53.685
Table 22 5.3.2 Situational awareness and forecasting | 5.3.2.7-2 | 5.3.2.7-2, Other, Meteorology Operations Center | 0 | 0 | 920.104 | 398.1394 | 0 | 0 | 0 | 0
Table 23 5.3.3 Grid design and system hardening | 5.3.3.1 | 5.3.3.1, Capacitor maintenance and replacement program | 1203.1018 | 1329.925 | 16353.0129 | 15412.0661 | 1363.1731 | 1397.2524 | 15797.3677 | 16192.3019
Table 23 5.3.3 Grid design and system hardening | 5.3.3.2-1 | 5.3.3.2-1, Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Non Enhanced - Maintenance Substation Distribution | 975.2769 | 1113.4428 | 3231.9577 | 2941.7484 | 1141.2789 | 1169.8109 | 3015.2921 | 3090.6744
Table 23 5.3.3 Grid design and system hardening | 5.3.3.2-2 | 5.3.3.2-2, Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Non Enhanced - Maintenance Substation Transmission | 0 | 0 | 20482.5774 | 25850.3662 | 0 | 0 | 26496.6254 | 27159.041
Table 23 5.3.3 Grid design and system hardening | 5.3.3.2-3 | 5.3.3.2-3, Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Enhanced - Maintenance Substation Distribution | 1823.1092 | 255.8395 | 12580.8889 | 3314.9498 | 262.2355 | 268.7914 | 3397.8236 | 3482.7692
Table 23 5.3.3 Grid design and system hardening | 5.3.3.2-4 | 5.3.3.2-4, Circuit breaker maintenance and installation to de-energize lines upon detecting a fault, Enhanced - Maintenance Substation Transmission | 1619.2987 | 194.8525 | 6482.7869 | 524.0968 | 199.7238 | 204.7169 | 537.1992 | 550.6292
Table 23 5.3.3 Grid design and system hardening | 5.3.3.3 | 5.3.3.3, Covered conductor installation | 0 | 0 | 25307.8153 | 17017 | 0 | 0 | 27566 | 34034
Table 23 5.3.3 Grid design and system hardening | 5.3.3.4 | 5.3.3.4, Covered conductor maintenance | 6127.4326 | 1329.801 | 3852.9991 | 6269.845 | 1363.046 | 1397.1222 | 6426.5911 | 6587.2559
Table 23 5.3.3 Grid design and system hardening | 5.3.3.5 | 5.3.3.5, Crossarm maintenance, repair, and replacement | 490.1391 | 218.8021 | 103811.6135 | 90276.3931 | 224.2722 | 229.879 | 118609.1779 | 136459.324
Table 23 5.3.3 Grid design and system hardening | 5.3.3.6 | 5.3.3.6, Distribution pole replacement and reinforcement, including with composite poles | 1502.2301 | 1563.2763 | 168642.2598 | 210914 | 1602.3582 | 1642.4172 | 216186.85 | 221591.5212
Table 23 5.3.3 Grid design and system hardening | 5.3.3.7 | 5.3.3.7, Expulsion fuse replacement | 0 | 0 | 7846.551 | 5423.125 | 0 | 0 | 5558.7031 | 5697.6707
Table 23 5.3.3 Grid design and system hardening | 5.3.3.8-1 | 5.3.3.8-1, Grid topology improvements to mitigate or reduce PSPS events, PSPS Granular Sectionalizing, Distribution | 0 | 0 | 70164.0146 | 83390 | 0 | 0 | 18311.9932 | 0
Table 23 5.3.3 Grid design and system hardening | 5.3.3.8-2 | 5.3.3.8-2, Grid topology improvements to mitigate or reduce PSPS events, Transmission Sectionalizing, Substation | 0 | 0 | 48850.3611 | 37183.6692 | 0 | 0 | 0 | 0
Table 23 5.3.3 Grid design and system hardening | 5.3.3.8-3 | 5.3.3.8-3, Grid topology improvements to mitigate or reduce PSPS events, Resilience Zones, Distribution | 0 | 0 | 13717.88 | 11178 | 0 | 0 | 12882.8716 | 15481.2
Table 23 5.3.3 Grid design and system hardening | 5.3.3.8-5 | 5.3.3.8-5, Grid topology improvements to mitigate or reduce PSPS events, Remote Grid, Distribution | 755.2311 | 943.3636 | 0 | 0 | 973.5293 | 1004.7005 | 0 | 0
Table 23 5.3.3 Grid design and system hardening | 5.3.3.9-1 | 5.3.3.9-1, Installation of system automation equipment, Expanded Automation | 10.1405 | 126.9207 | 1405.141 | 3780 | 130.4231 | 133.9256 | 0 | 0
Table 23 5.3.3 Grid design and system hardening | 5.3.3.9-2 | 5.3.3.9-2, Installation of system automation equipment, Fuse Saver, Distribution | 0 | 0 | 0 | 3486.665 | 0 | 0 | 3990.7577 | 4030.544
Table 23 5.3.3 Grid design and system hardening | 5.3.3.9-3 | 5.3.3.9-3, Installation of system automation equipment, Installation of system automation equipment, Distribution and Distribution Substation | 0 | 0 | 3157.7958 | 4087.2123 | 0 | 0 | 4189.3926 | 4294.1275
Table 23 5.3.3 Grid design and system hardening | 5.3.3.10 | 5.3.3.10, Maintenance, repair, and replacement of connectors, including hotline clamps, Distribution, Transmission, and System Hardening | 6906.6015 | 2648.591 | 50859.5842 | 39257.5268 | 2714.8058 | 2782.676 | 60179.34 | 73066.4068
Table 23 5.3.3 Grid design and system hardening | 5.3.3.11-1 | 5.3.3.11-1, Mitigation of impact on customers and other residents affected during PSPS event, Distributed Generation Enabled Microgrids (DGEMs) | 131656 | 46769.2308 | 6239 | 99000.0025 | 0 | 0 | 0 | 0
Table 23 5.3.3 Grid design and system hardening | 5.3.3.11-2 | 5.3.3.11-2, Mitigation of impact on customers and other residents affected during PSPS event, PSPS Control only (substation) | 0 | 0 | 3879.0183 | 9945.5368 | 0 | 0 | 10194.1752 | 10449.0296
Table 23 5.3.3 Grid design and system hardening | 5.3.3.12-1 | 5.3.3.12-1, Other corrective action, Distribution Substation | 0 | 0 | 851.1604 | 492.7234 | 0 | 0 | 505.0415 | 517.6676
Table 23 5.3.3 Grid design and system hardening | 5.3.3.12-2 | 5.3.3.12-2, Other corrective action, Transmission substation | 0 | 0 | 7216.6805 | 10629.578 | 0 | 0 | 10895.3174 | 11167.7003
Table 23 5.3.3 Grid design and system hardening | 5.3.3.12-3 | 5.3.3.12-3, Other corrective action, Non-Enhanced maintenance transmission | 10947.7905 | 11297.4288 | 107268.5247 | 158096.4203 | 11579.8645 | 11869.3611 | 162048.8308 | 166100.0516
Table 23 5.3.3 Grid design and system hardening | 5.3.3.12-4 | 5.3.3.12-4, Other corrective action, Enhanced maintenance distribution | 52600.4523 | 22289.0518 | 70426.7377 | 117703.7846 | 22846.2781 | 23417.4351 | 120646.3792 | 123662.5387
Table 23 5.3.3 Grid design and system hardening | 5.3.3.13 | 5.3.3.13, Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 61.0714 | 829.5205 | 2656.2675 | 2575.5392 | 149.1 | 153.874 | 0 | 0
Table 23 5.3.3 Grid design and system hardening | 5.3.3.14 | 5.3.3.14, Transformers maintenance and replacement | 25.7681 | 15.397 | 48026.8832 | 36661.989 | 15.7819 | 16.1765 | 53224.0637 | 63485.6153
Table 23 5.3.3 Grid design and system hardening | 5.3.3.15 | 5.3.3.15, Transmission tower maintenance and replacement | 61946.1941 | 66475.3993 | 204544.0711 | 217536.4972 | 68137.2843 | 69840.7164 | 222974.9096 | 228549.2823
Table 23 5.3.3 Grid design and system hardening | 5.3.3.16 | 5.3.3.16, Undergrounding of electric lines and/or equipment | 0 | 0 | 0 | 0 | 0 | 0 | 89500 | 110500
Table 23 5.3.3 Grid design and system hardening | 5.3.3.17-1 | 5.3.3.17-1, Updates to grid topology to minimize risk of ignition in HFTDs, System Hardening, Distribution | 0 | 0 | 280686.6783 | 246058.6389 | 0 | 0 | 280672 | 346528
Table 23 5.3.3 Grid design and system hardening | 5.3.3.17-2 | 5.3.3.17-2, Updates to grid topology to minimize risk of ignition in HFTDs, Surge Arrestor | 0 | 0 | 63497.9185 | 62448.245 | 0 | 0 | 53289.837 | 0
Table 23 5.3.3 Grid design and system hardening | 5.3.3.17-3 | 5.3.3.17-3, Updates to grid topology to minimize risk of ignition in HFTDs, EPIC - Rapid Earth Current Fault Limiter, Distribution | 6425.33 | 5022.99 | 4798.22 | 0 | 0 | 0 | 9461.7 | 9711
Table 23 5.3.3 Grid design and system hardening | 5.3.3.18 | 5.3.3.18, Other/not listed, Building and Sourcing Services- Transmission and Distribution | 544.5578 | 1029.4 | 38390.6442 | 10270 | 5297.5 | 5451.5 | 5279 | 5432
Table 24 5.3.4 Asset management and inspections | 5.3.4.1 | 5.3.4.1, Detailed inspections of distribution electric lines and equipment, Non-Enhanced | 898.2053 | 1005.9027 | 0 | 0 | 1031.0503 | 1056.8265 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.2 | 5.3.4.2, Detailed inspections of transmission electric lines and equipment, Non Enhanced | 1121.0204 | 413.3331 | 0 | 0 | 423.6664 | 434.2581 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.3 | 5.3.4.3, Improvement of inspections | 223.8438 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.4 | 5.3.4.4, Infrared inspections of distribution electric lines and equipment | 495.9115 | 696.5408 | 0 | 0 | 713.9543 | 731.8032 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.5 | 5.3.4.5, Infrared inspections of transmission electric lines and equipment | 170.9543 | 236.0867 | 0 | 0 | 241.9888 | 248.0385 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.6 | 5.3.4.6, Intrusive pole inspections, Intrusive pole inspections | 5541.4107 | 4629.7311 | 0 | 0 | 4745.4743 | 4864.1112 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.9 | 5.3.4.9, Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations, Enhanced Distribution | 82723.7607 | 93178.2564 | 0 | 0 | 95507.7129 | 97895.4057 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.10 | 5.3.4.10, Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations, Enhanced Transmission | 40765.6131 | 60052.4351 | 0 | 0 | 61553.746 | 63092.5897 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.11 | 5.3.4.11, Patrol inspections of distribution electric lines and equipment | 2735.4119 | 4874.1664 | 0 | 0 | 4996.0206 | 5120.9211 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.12 | 5.3.4.12, Patrol inspections of transmission electric lines and equipment | 0 | 60.5505 | 0 | 0 | 62.0642 | 63.6158 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.13 | 5.3.4.13, Pole loading assessment program to determine safety factor | 18604.3079 | 38000 | 0 | 0 | 38950 | 39923.75 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.14 | 5.3.4.14, Quality assurance / quality control of inspections | 1831.4492 | 4389.4436 | 0 | 0 | 4499.1796 | 4611.6591 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.15-1 | 5.3.4.15-1, Substation inspections, Enhanced Transmission, Substation | 6726.5166 | 6925.6247 | 0 | 0 | 7098.7654 | 7276.2345 | 0 | 0
Table 24 5.3.4 Asset management and inspections | 5.3.4.15-2 | 5.3.4.15-2, Substation inspections, Enhanced Distribution Substation | 4618.6778 | 2066.8513 | 0 | 0 | 2118.5225 | 2171.4856 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.1 | 5.3.5.1, Additional efforts to manage community and environmental impacts | 8944.0641 | 9797.281 | 0 | 0 | 10011.7414 | 10232.0691 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.2 | 5.3.5.2, Detailed inspections of vegetation around distribution electric lines and equipment | 77453.2206 | 59644.8052 | 0 | 0 | 61434.1494 | 63277.1739 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.3 | 5.3.5.3, Detailed inspections of vegetation around transmission electric lines and equipment | 11456.1974 | 13051.9112 | 0 | 0 | 12995.2869 | 12936.964 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.4 | 5.3.5.4, Emergency response vegetation management due to red flag warning or other urgent conditions | 2420.973 | 1964.2586 | 0 | 0 | 2012.5982 | 2062.3879 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.5 | 5.3.5.5, Fuel management and reduction of “slash” from vegetation management activities | 5168.32 | 25000 | 0 | 0 | 25625 | 26265.625 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.6 | 5.3.5.6, Improvement of inspections | 8616.5028 | 5687.5553 | 0 | 0 | 5858.182 | 6033.9274 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.7.1 | 5.3.5.7.1, LiDAR inspections of vegetation around distribution electric lines and equipment, Enhanced Vegetation Management, Distribution | 4450.46 | 7155 | 0 | 0 | 7369.65 | 7590.7395 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.7.2 | 5.3.5.7.2, LiDAR inspections of vegetation around distribution electric lines and equipment, Routine Vegetation Management, Distribution | 103.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.8 | 5.3.5.8, LiDAR inspections of vegetation around transmission electric lines and equipment | 2820.6583 | 5597.497 | 0 | 0 | 5765.4219 | 5938.3845 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.9 | 5.3.5.9, Other discretionary inspections of vegetation around distribution electric lines and equipment | 3315.0922 | 4846.0684 | 0 | 0 | 15769.2108 | 16242.2871 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.10 | 5.3.5.10, Other discretionary inspections of vegetation around transmission electric lines and equipment | 78.7217 | 89.6867 | 0 | 0 | 89.2976 | 88.8969 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.11 | 5.3.5.11, Patrol inspections of vegetation around distribution electric lines and equipment | 102059.8145 | 105348.6497 | 0 | 0 | 108147.9083 | 111022.1146 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.12 | 5.3.5.12, Patrol inspections of vegetation around transmission electric lines and equipment | 33509.6756 | 35892.5262 | 0 | 0 | 36623.126 | 37371.6633 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.13 | 5.3.5.13, Quality assurance / quality control of vegetation inspections, Enhanced, Routine, CEMA | 24618.5794 | 10562.6027 | 0 | 0 | 10879.4808 | 11205.8652 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.14 | 5.3.5.14, Recruiting and training of vegetation management personnel | 2197.4938 | 1861.0756 | 0 | 0 | 1899.0178 | 1938.0983 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.15 | 5.3.5.15, Remediation of at-risk species, Enhanced Vegetation Management | 92987.5117 | 98545.2849 | 0 | 0 | 100986.3225 | 103487.7083 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.16 | 5.3.5.16, Removal and remediation of trees with strike potential to electric lines and equipment, Transmission | 0 | 0 | 14290.5914 | 14638.5346 | 0 | 0 | 15004.4979 | 15379.6104
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.17-1 | 5.3.5.17-1, Substation inspection, Enhanced Substation Maintenance Vegetation, Distribution Substation | 293.552 | 812 | 0 | 0 | 832.3 | 853.1075 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.17-2 | 5.3.5.17-2, Substation inspection, Enhanced Substation Maintenance Vegetation, Transmission Substation | 159.355 | 348 | 0 | 0 | 356.7 | 365.6175 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.18-1 | 5.3.5.18-1, Substation vegetation management, Enhanced maintenance, Substation Distribution | 3118.3157 | 862.1392 | 0 | 0 | 883.6927 | 905.785 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.18-2 | 5.3.5.18-2, Substation vegetation management, Enhanced maintenance, Substation Transmission | 1414.9556 | 1026.9226 | 0 | 0 | 1052.5957 | 1078.9106 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.19 | 5.3.5.19, Vegetation inventory system | 5185.4672 | 4974.9473 | 0 | 0 | 5105.4149 | 5239.3271 | 0 | 0
Table 25 5.3.5 Vegetation management and inspections | 5.3.5.20 | 5.3.5.20, Vegetation management to achieve clearances around electric lines and equipment | 423982.0721 | 438311.0585 | 0 | 0 | 438740.9726 | 449929.7706 | 0 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.1 | 5.3.6.1, Automatic recloser operations | 36 | 3.4656 | 0 | 0 | 3.5522 | 3.641 | 0 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.2 | 5.3.6.2, Crew-accompanying ignition prevention and suppression resources and services | 9205.1416 | 14200.5993 | 1253.9252 | 675.84 | 22233.9108 | 24771.5266 | 1152.36 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.3 | 5.3.6.3, Personnel work procedures and training in conditions of elevated fire risk | 839.8231 | 1235.28 | 0 | 0 | 317.85 | 327.09 | 0 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.4-1 | 5.3.6.4-1, Protocols for PSPS re-energization, Distribution | 61369.9618 | 11830.6325 | 1021 | 0 | 12126.3983 | 12429.5582 | 0 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.4-2 | 5.3.6.4-2, Protocols for PSPS re-energization, Transmission | 1329 | 1027.424 | 0 | 0 | 1053.1096 | 1079.4373 | 0 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.5-1 | 5.3.6.5-1, PSPS events and mitigation of PSPS impacts, Distribution | 80462 | 139044.936 | 0 | 0 | 142521.0594 | 146084.0859 | 0 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.5-2 | 5.3.6.5-2, PSPS events and mitigation of PSPS impacts, Transmission | 350 | 14568.296 | 0 | 0 | 14932.5034 | 15305.816 | 0 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.5-3 | 5.3.6.5-3, PSPS events and mitigation of PSPS impacts, Additional PSPS Mitigation Initiatives, Distribution | 0 | 48334.644 | 0 | 8410 | 49543.0101 | 50781.5854 | 0 | 0
Table 26 5.3.6 Grid operations and protocols | 5.3.6.6 | 5.3.6.6, Stationed and on-call ignition prevention and suppression resources and services | 3068.3805 | 4733.5331 | 0 | 0 | 7411.3036 | 8257.1755 | 0 | 0
Table 27 5.3.7 Data governance | 5.3.7.1 | 5.3.7.1, Centralized repository for data | 841.612 | 291.0437 | 0 | 0 | 267.1822 | 257.9038 | 0 | 0
Table 27 5.3.7 Data governance | 5.3.7.2 | 5.3.7.2, Collaborative research on utility ignition and/or wildfire | 1457.7518 | 1143.18 | 0 | 0 | 773.443 | 478.0344 | 0 | 0
Table 27 5.3.7 Data governance | 5.3.7.3 | 5.3.7.3, Documentation and disclosure of wildfire-related data and algorithms | 420.806 | 521.3312 | 0 | 0 | 503.2269 | 499.8496 | 0 | 0
Table 27 5.3.7 Data governance | 5.3.7.4 | 5.3.7.4, Tracking and analysis of near miss data | 723.3121 | 788.2596 | 0 | 0 | 807.9661 | 828.1652 | 0 | 0
Table 27 5.3.7 Data governance | 5.3.7.5 | 5.3.7.5, Other, Information Technology, Transmission and Distribution | 46464.1706 | 46399.296 | 66711.555 | 41831.665 | 43236.373 | 34402.0091 | 6386.6409 | 4881.0048
Table 28 5.3.8 Resource allocation methodology | 5.3.8.1 | 5.3.8.1, Allocation methodology development and application | 4117.9849 | 1639.416 | 0 | 0 | 1680.4014 | 1722.4115 | 0 | 0
Table 28 5.3.8 Resource allocation methodology | 5.3.8.2 | 5.3.8.2, Risk reduction scenario development and analysis | 712.1583 | 270.9117 | 0 | 0 | 277.6845 | 284.6266 | 0 | 0
Table 28 5.3.8 Resource allocation methodology | 5.3.8.3 | 5.3.8.3, Risk spend efficiency analysis | 1760.3915 | 237.5358 | 0 | 0 | 243.4742 | 249.561 | 0 | 0
Table 29 5.3.9 Emergency planning and preparedness | 5.3.9.1 | 5.3.9.1, Adequate and trained workforce for service restoration | 1842.9107 | 1451.7296 | 0 | 0 | 1488.0229 | 1525.2234 | 0 | 0
Table 29 5.3.9 Emergency planning and preparedness | 5.3.9.2 | 5.3.9.2, Community outreach, public awareness, and communications effort | 6477.669 | 7700.8917 | 0 | 0 | 7893.414 | 8090.7493 | 0 | 0
Table 29 5.3.9 Emergency planning and preparedness | 5.3.9.3 | 5.3.9.3, Customer support in emergencies | 3712.1701 | 3100 | 0 | 0 | 3177.5 | 3256.9375 | 0 | 0
Table 29 5.3.9 Emergency planning and preparedness | 5.3.9.4 | 5.3.9.4, Disaster and emergency preparedness plan | 7666 | 20709.7446 | 1909.872 | 5000 | 21227.4882 | 21758.1754 | 5125 | 5253.125
Table 29 5.3.9 Emergency planning and preparedness | 5.3.9.5 | 5.3.9.5, Preparedness and planning for service restoration | 3685.8215 | 2903.4592 | 0 | 0 | 2976.0457 | 3050.4469 | 0 | 0
Table 29 5.3.9 Emergency planning and preparedness | 5.3.9.6 | 5.3.9.6, Protocols in place to learn from wildfire events | 2027.2018 | 1596.9026 | 0 | 0 | 1636.8251 | 1677.7458 | 0 | 0
Table 29 5.3.9 Emergency planning and preparedness | 5.3.9.7 | 5.3.9.7, Other, Aviation Support | 5397.5698 | 2156.1782 | 480.5551 | 0 | 2225.1258 | 2296.3716 | 0 | 0
Table 30 5.3.10 Stakeholder cooperation and community engagement | 5.3.10.1 | 5.3.10.1, Community engagement | 9513.653 | 11370.8917 | 0 | 0 | 11655.164 | 11946.5431 | 0 | 0
Table 30 5.3.10 Stakeholder cooperation and community engagement | 5.3.10.2 | 5.3.10.2, Cooperation and best practice sharing with agencies outside CA | 12.5 | 6.0219 | 0 | 0 | 6.1724 | 6.3267 | 0 | 0
Table 30 5.3.10 Stakeholder cooperation and community engagement | 5.3.10.3 | 5.3.10.3, Cooperation with suppression agencies | 4000 | 7501.0334 | 0 | 0 | 8849.237 | 9132.5788 | 0 | 0
Table 30 5.3.10 Stakeholder cooperation and community engagement | 5.3.10.4 | 5.3.10.4, Forest service and fuel reduction cooperation and joint roadmap | 2687.3067 | 3133.0612 | 0 | 0 | 3211.3877 | 3291.6724 | 0 | 0
Table 30 5.3.10 Stakeholder cooperation and community engagement | 5.3.10.5-1 | 5.3.10.5-1, Other, PMO | 17753.3898 | 7529.2 | 0 | 0 | 7796 | 8068.525 | 0 | 0
Table 30 5.3.10 Stakeholder cooperation and community engagement | 5.3.10.5-2 | 5.3.10.5-2, Other, Emergency Outreach campaigns | 7592 | 7720.5 | 0 | 0 | 8177.25 | 8177.25 | 0 | 0
|  | Total | 1584289.3015 | 1608150.4043 | 1494536.2348 | 1616144.3298 | 1608101.7804 | 1640310.5354 | 1581876.3744 | 1660767.4047