## As of 12.31 (In Scope)
Column 1: Circuit Name | Column 2: Circuit Protection Zone | Column 3: Remaining EVM Miles - 1/1/2021 | Column 4: Forecasted Tree Work | Column 5: Tree Weighted Risk Score | Column 6: Tree Weighted Rank | Column 7: Plan (Mile Cutoff) | Column 8: Risk Tranche | Column 9: Miles Complete and Verified as of 12/31/21 (Audited) | Column 10: Miles Work Verified with No Overhead Present as of 12/31/21 (Audited) | Column 11: Miles Ready for Work Verification as of 12/31/21 (Unaudited) | Column 12: Miles Constrained as of 12/31/21 (Unaudited) | Column 13: Remaining EVM Miles - 12/31/21 (Unaudited)
RIO DELL 1102 | RIO DELL 11024230 | 22.8243 | 4236.5992 | 202.0407 | 1 | 1800 MILE | 1. <= 10% | 9.6298 | 0 | 1.8076 | 11.2241 | 0.16284
APPLE HILL 2102 | APPLE HILL 2102circuit_breaker | 38.4116 | 4581.5731 | 175.1558 | 2 | 1800 MILE | 1. <= 10% | 30.2835 | 0.067042 | 0.16698 | 6.7348 | 1.1593
FORT SEWARD 1121 | FORT SEWARD 11211690 | 10.4326 | 1715.0064 | 153.252 | 3 | 1800 MILE | 1. <= 10% | 8.5149 | 0 | 0 | 1.3485 | 0.56921
OAKHURST 1101 | OAKHURST 110110090 | 31.3792 | 1754.7268 | 134.5826 | 4 | 1800 MILE | 1. <= 10% | 23.3512 | 0.13228 | 0 | 3.0179 | 4.8778
OREGON TRAIL 1104 | OREGON TRAIL 11041574 | 15.861 | 629.4627 | 133.2708 | 5 | 1800 MILE | 1. <= 10% | 11.7465 | 0.035654 | 0 | 3.499 | 0.57989
MIDDLETOWN 1101 | MIDDLETOWN 1101622 | 12.0484 | 939.1786 | 129.2464 | 6 | 1800 MILE | 1. <= 10% | 6.5194 | 0 | 0.22062 | 3.7317 | 1.5767
BIG BEND 1102 | BIG BEND 11021972 | 21.0591 | 4537.6749 | 122.6772 | 7 | 1800 MILE | 1. <= 10% | 1.4374 | 17.8983 | 0 | 1.7234 | 4.4409e-15
DESCHUTES 1104 | DESCHUTES 11041370 | 14.7261 | 481.7941 | 119.3721 | 8 | 1800 MILE | 1. <= 10% | 11.7547 | 0.033109 | 0.054852 | 1.3564 | 1.5271
DESCHUTES 1101 | DESCHUTES 11011580 | 45.359 | 2608.4836 | 115.4797 | 9 | 1800 MILE | 1. <= 10% | 36.4193 | 0.21348 | 0.056494 | 6.5876 | 2.0822
HIGGINS 1109 | HIGGINS 110950072 | 50.9379 | 2058.0358 | 109.8342 | 10 | 1800 MILE | 1. <= 10% | 39.0431 | 0.14205 | 0.22903 | 10.6085 | 0.91515
DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11057722 | 47.8497 | 2812.3526 | 108.1002 | 11 | 1800 MILE | 1. <= 10% | 50.4219 | 0.030424 | 0 | 8.4474 | 0
OREGON TRAIL 1104 | OREGON TRAIL 11041634 | 17.0008 | 444.451 | 105.891 | 12 | 1800 MILE | 1. <= 10% | 13.5097 | 0.13873 | 0 | 3.2031 | 0.1493
CHALLENGE 1102 | CHALLENGE 11021064 | 20.3014 | 3727.1699 | 105.1309 | 13 | 1800 MILE | 1. <= 10% | 10.1474 | 0.029437 | 0.86171 | 8.7218 | 0.54107
BANGOR 1101 | BANGOR 11017446 | 28.4677 | 4060.5445 | 103.4169 | 14 | 1800 MILE | 1. <= 10% | 22.7311 | 0.063309 | 0.074092 | 3.1759 | 2.4233
VACA DIXON 1105 | VACA DIXON 110540092 | 24.4629 | 418.2334 | 102.3868 | 15 | 1800 MILE | 1. <= 10% | 21.1647 | 0 | 0.051682 | 1.7963 | 1.4502
MARIPOSA 2102 | MARIPOSA 210210880 | 39.2457 | 901.8883 | 101.3631 | 16 | 1800 MILE | 1. <= 10% | 36.1196 | 0.87906 | 0.25246 | 1.5052 | 0.48938
SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210913322 | 40.3986 | 1742.5409 | 99.5875 | 17 | 1800 MILE | 1. <= 10% | 37.8252 | 0.045433 | 0.13428 | 2.2424 | 0.15131
AUBERRY 1101 | AUBERRY 1101R2578 | 42.3462 | 1543.2887 | 99.4645 | 18 | 1800 MILE | 1. <= 10% | 36.7019 | 0.4415 | 0 | 1.8107 | 3.3921
WISE 1102 | WISE 11022230 | 23.8886 | 705.05 | 97.2018 | 19 | 1800 MILE | 1. <= 10% | 21.1436 | 0.0039528 | 0 | 1.2054 | 1.5357
OREGON TRAIL 1104 | OREGON TRAIL 1104circuit_breaker | 10.7202 | 659.8509 | 95.2297 | 20 | 1800 MILE | 1. <= 10% | 7.5061 | 0.058173 | 0 | 2.8 | 0.35595
UKIAH 1111 | UKIAH 1111534 | 18.2775 | 1145.6293 | 90.9972 | 21 | 1800 MILE | 1. <= 10% | 15.5359 | 0.2985 | 0.041466 | 2.6218 | 0
CEDAR CREEK 1101 | CEDAR CREEK 11011664 | 28.9265 | 2298.2056 | 90.0697 | 22 | 1800 MILE | 1. <= 10% | 16.2943 | 0.073307 | 0.48183 | 11.8345 | 0.24259
PUEBLO 2103 | PUEBLO 2103678 | 34.569 | 3953.4629 | 89.8508 | 23 | 1800 MILE | 1. <= 10% | 20.8866 | 0.12654 | 0.53081 | 11.1578 | 1.8673
STILLWATER 1102 | STILLWATER 1102circuit_breaker | 24.4011 | 1386.8379 | 89.6142 | 24 | 1800 MILE | 1. <= 10% | 20.1916 | 0.2559 | 0.29614 | 3.6141 | 0.043368
DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | 35.1198 | 1931.3848 | 88.1926 | 25 | 1800 MILE | 1. <= 10% | 31.0735 | 0.030376 | 0.046942 | 6.9806 | 0
BRIDGEVILLE 1102 | BRIDGEVILLE 1102circuit_breaker | 25.2673 | 2534.2404 | 84.1943 | 26 | 1800 MILE | 1. <= 10% | 18.9848 | 0 | 0.15589 | 5.494 | 0.63253
HIGGINS 1109 | HIGGINS 1109circuit_breaker | 26.3378 | 1247.1931 | 82.5012 | 27 | 1800 MILE | 1. <= 10% | 22.8712 | 0.12802 | 0.10231 | 2.7666 | 0.46965
PIKE CITY 1101 | PIKE CITY 1101circuit_breaker | 19.4168 | 4458.0897 | 80.9942 | 28 | 1800 MILE | 1. <= 10% | 9.1734 | 0.15551 | 0.72859 | 8.3789 | 0.98048
GARBERVILLE 1102 | GARBERVILLE 110256048 | 4.8438 | 2568.2874 | 79.6963 | 29 | 1800 MILE | 1. <= 10% | 4.366 | 0 | 0.053458 | 0.35306 | 0.071321
CEDAR CREEK 1101 | CEDAR CREEK 11011656 | 31.3055 | 4190.4761 | 79.0101 | 30 | 1800 MILE | 1. <= 10% | 9.8915 | 0.0083679 | 1.1099 | 19.7974 | 0.49834
FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 20.5952 | 3310.7203 | 78.2612 | 31 | 1800 MILE | 1. <= 10% | 5.9227 | 2.3635 | 0.37262 | 11.6886 | 0.24783
RED BLUFF 1101 | RED BLUFF 11011334 | 39.9743 | 674.1903 | 77.9097 | 32 | 1800 MILE | 1. <= 10% | 34.8536 | 0.014749 | 0 | 4.5816 | 0.52436
LAYTONVILLE 1102 | LAYTONVILLE 1102500 | 14.7132 | 1702.7298 | 74.6115 | 33 | 1800 MILE | 1. <= 10% | 11.6808 | 0.012641 | 0.72159 | 2.201 | 0.097205
OAKHURST 1103 | OAKHURST 1103circuit_breaker | 30.2126 | 1548.4954 | 74.356 | 34 | 1800 MILE | 1. <= 10% | 22.8329 | 0.071519 | 0.12614 | 2.1145 | 5.0675
MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101circuit_breaker | 25.8396 | 918.8619 | 72.7336 | 35 | 1800 MILE | 1. <= 10% | 25.0147 | 0 | 0.14139 | 0.51318 | 0.17036
VACAVILLE 1108 | VACAVILLE 110838316 | 16.5822 | 403.8228 | 72.2638 | 36 | 1800 MILE | 1. <= 10% | 14.6868 | 0.014042 | 0 | 0.6644 | 1.217
CEDAR CREEK 1101 | CEDAR CREEK 11011608 | 32.9031 | 2930.8477 | 71.5126 | 37 | 1800 MILE | 1. <= 10% | 18.596 | 0.094726 | 1.998 | 12.1895 | 0.024863
BELL 1107 | BELL 11072400 | 10.0506 | 800.4196 | 69.053 | 38 | 1800 MILE | 1. <= 10% | 8.448 | 0.014963 | 0 | 1.3289 | 0.25879
PHILO 1101 | PHILO 110137222 | 24.4987 | 1347.3546 | 68.463 | 39 | 1800 MILE | 1. <= 10% | 18.4873 | 0.12075 | 0.76473 | 4.6365 | 0.48945
SAN JOAQUIN NO2 1103 | SAN JOAQUIN #2 1103circuit_breaker | 67.3142 | 1543.7475 | 67.2353 | 40 | 1800 MILE | 1. <= 10% | 62.7666 | 0.22413 | 0.46417 | 4.1223 | 0
SALMON CREEK 1101 | SALMON CREEK 110188998 | 7.6341 | 523.0723 | 66.338 | 41 | 1800 MILE | 1. <= 10% | 5.6653 | 0 | 0 | 1.5232 | 0.44562
FRUITLAND 1142 | FRUITLAND 114293234 | 10.6913 | 1938.3143 | 66.0004 | 42 | 1800 MILE | 1. <= 10% | 7.313 | 0 | 0.2804 | 3.1714 | 0
DESCHUTES 1104 | DESCHUTES 110449024 | 16.0327 | 274.0379 | 65.9336 | 43 | 1800 MILE | 1. <= 10% | 14.5289 | 0 | 0.030999 | 1.2132 | 0.25966
AUBERRY 1102 | AUBERRY 1102circuit_breaker | 33.2505 | 517.3344 | 65.7109 | 44 | 1800 MILE | 1. <= 10% | 31.0762 | 0.64299 | 0 | 1.683 | 0
STILLWATER 1102 | STILLWATER 110248952 | 10.654 | 501.3323 | 64.1905 | 45 | 1800 MILE | 1. <= 10% | 8.1735 | 0.0029114 | 0 | 2.1499 | 0.32774
OAKHURST 1103 | OAKHURST 110363334 | 15.2674 | 534.4575 | 63.9375 | 46 | 1800 MILE | 1. <= 10% | 14.4987 | 0.033073 | 0 | 0.32778 | 0.40789
BELL 1108 | BELL 11082202 | 29.4283 | 891.931 | 63.8696 | 47 | 1800 MILE | 1. <= 10% | 25.1909 | 0.058625 | 0.053218 | 1.7523 | 2.3732
WYANDOTTE 1109 | WYANDOTTE 110979932 | 21.145 | 630.6093 | 63.4787 | 48 | 1800 MILE | 1. <= 10% | 20.269 | 0.0028415 | 0 | 0.6832 | 0.18993
WILLITS 1103 | WILLITS 110391810 | 27.1347 | 3745.7704 | 62.6524 | 49 | 1800 MILE | 1. <= 10% | 16.9684 | 0.05794 | 0.11629 | 11.4473 | 0
GEYSERVILLE 1101 | GEYSERVILLE 1101166 | 11.1278 | 1016.1042 | 62.2023 | 50 | 1800 MILE | 1. <= 10% | 6.3379 | 0.10603 | 0.15384 | 4.4473 | 0.082701
WOODSIDE 1101 | WOODSIDE 11018974 | 11.5494 | 4187.5325 | 62.1631 | 51 | 1800 MILE | 1. <= 10% | 4.1275 | 0.042306 | 0 | 5.5071 | 1.8725
SILVERADO 2104 | SILVERADO 2104632 | 7.5905 | 742.0887 | 61.8094 | 52 | 1800 MILE | 1. <= 10% | 3.3122 | 0.44775 | 0.49665 | 3.1327 | 0.20122
MARIPOSA 2102 | MARIPOSA 210237282 | 52.1381 | 1212.9266 | 60.8076 | 53 | 1800 MILE | 1. <= 10% | 43.6474 | 1.0554 | 0.082417 | 4.1605 | 3.1924
DESCHUTES 1104 | DESCHUTES 11049718 | 20.5895 | 421.883 | 60.5428 | 54 | 1800 MILE | 1. <= 10% | 14.272 | 0.042837 | 0.48113 | 1.7543 | 4.0392
OAKHURST 1101 | OAKHURST 11015490 | 10.5001 | 497.1859 | 59.4702 | 55 | 1800 MILE | 1. <= 10% | 11.3406 | 0.009506 | 0.10406 | 2.4708 | 0
COTTONWOOD 1101 | COTTONWOOD 110168190 | 23.866 | 602.7591 | 58.3616 | 56 | 1800 MILE | 1. <= 10% | 20.4413 | 0 | 0.25537 | 2.7374 | 0.43191
PHILO 1101 | PHILO 1101circuit_breaker | 32.4872 | 2622.5897 | 57.8128 | 57 | 1800 MILE | 1. <= 10% | 6.6135 | 0.1267 | 0.041188 | 24.5079 | 1.1979
STILLWATER 1102 | STILLWATER 11021644 | 22.7735 | 905.9803 | 56.9 | 58 | 1800 MILE | 1. <= 10% | 19.6507 | 0.073614 | 0.11135 | 2.7358 | 0.20203
COARSEGOLD 2103 | COARSEGOLD 210310820 | 27.5985 | 467.8236 | 56.4857 | 59 | 1800 MILE | 1. <= 10% | 27.4674 | 0.12291 | 0 | 0.36876 | 0
APPLE HILL 2102 | APPLE HILL 21021532 | 37.0732 | 3569.7143 | 56.0389 | 60 | 1800 MILE | 1. <= 10% | 27.4116 | 0 | 0.046615 | 7.8284 | 1.7866
GIRVAN 1101 | GIRVAN 1101323094 | 35.307 | 1389.3096 | 55.6591 | 61 | 1800 MILE | 1. <= 10% | 26.9393 | 1.3707 | 0.25308 | 4.6248 | 2.1191
LAYTONVILLE 1102 | LAYTONVILLE 1102572 | 20.6201 | 2694.9485 | 55.5272 | 62 | 1800 MILE | 1. <= 10% | 12.3807 | 0.3737 | 1.1733 | 5.9705 | 0.72177
PIKE CITY 1102 | PIKE CITY 1102circuit_breaker | 9.4152 | 2708.5399 | 55.3285 | 63 | 1800 MILE | 1. <= 10% | 1.4143 | 0 | 0.15293 | 7.8122 | 0.035754
BROWNS VALLEY 1101 | BROWNS VALLEY 110193870 | 20.8292 | 564.971 | 55.0784 | 64 | 1800 MILE | 1. <= 10% | 17.442 | 0.027422 | 0 | 0.28291 | 3.0768
ANTLER 1101 | ANTLER 11011378 | 24.2697 | 2949.3702 | 54.0137 | 65 | 1800 MILE | 1. <= 10% | 6.0273 | 0 | 0.039303 | 17.5789 | 0.62425
CHALLENGE 1102 | CHALLENGE 1102circuit_breaker | 14.6708 | 3651.3224 | 53.4535 | 66 | 1800 MILE | 1. <= 10% | 4.3727 | 0.007952 | 0.67317 | 9.4492 | 0.16782
LAYTONVILLE 1102 | LAYTONVILLE 110237586 | 13.8802 | 1272.3323 | 52.81 | 67 | 1800 MILE | 1. <= 10% | 8.2511 | 0.085181 | 0.39 | 5.7298 | 0
HOOPA 1101 | HOOPA 11013290 | 12.8576 | 1552.9435 | 52.5617 | 68 | 1800 MILE | 1. <= 10% | 1.8446 | 0.017586 | 0.21294 | 11.5866 | 0
PENRYN 1105 | PENRYN 11051342 | 22.493 | 877.4866 | 52.3738 | 69 | 1800 MILE | 1. <= 10% | 15.4516 | 0.22022 | 0 | 4.9911 | 1.8301
KANAKA 1101 | KANAKA 110165606 | 12.843 | 3194.7238 | 51.4012 | 70 | 1800 MILE | 1. <= 10% | 3.0407 | 0.0044661 | 0.40184 | 9.3086 | 0.087488
LINCOLN 1104 | LINCOLN 11042070 | 20.6137 | 602.8487 | 50.4992 | 71 | 1800 MILE | 1. <= 10% | 15.6542 | 0.04713 | 0.077737 | 1.2592 | 3.5754
WYANDOTTE 1103 | WYANDOTTE 11031974 | 23.007 | 4221.0833 | 49.6264 | 72 | 1800 MILE | 1. <= 10% | 2.3494 | 17.3714 | 0 | 0.63659 | 2.6496
COTTONWOOD 1102 | COTTONWOOD 11021578 | 29.4879 | 1137.091 | 49.5381 | 73 | 1800 MILE | 1. <= 10% | 19.7176 | 0.002842 | 0.091274 | 5.4599 | 4.2163
PENRYN 1103 | PENRYN 11032198 | 16.8137 | 594.7357 | 48.9082 | 74 | 1800 MILE | 1. <= 10% | 14.9053 | 0.012948 | 0 | 0.67262 | 1.2228
LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 5.436 | 739.2427 | 48.8439 | 75 | 1800 MILE | 1. <= 10% | 2.6752 | 0 | 0.2711 | 2.3286 | 0.1611
PLACERVILLE 2106 | PLACERVILLE 21067522 | 65.1893 | 6799.4932 | 48.7602 | 76 | 1800 MILE | 1. <= 10% | 57.1651 | 0.10847 | 0.076962 | 7.7037 | 0.13508
DESCHUTES 1104 | DESCHUTES 11049726 | 14.6404 | 255.1909 | 48.6822 | 77 | 2400 MILE | 1. <= 10% | 13.3858 | 0.02732 | 0 | 1.0457 | 0.18162
GRASS VALLEY 1103 | GRASS VALLEY 11032180 | 44.1891 | 2408.3511 | 48.3542 | 78 | 2400 MILE | 1. <= 10% | 36.081 | 0.11425 | 0.37879 | 6.4542 | 1.1609
HIGGINS 1109 | HIGGINS 110950078 | 46.9656 | 844.7903 | 47.4732 | 79 | 2400 MILE | 1. <= 10% | 43.6257 | 0.17348 | 0.058786 | 2.8716 | 0.23598
HOOPA 1101 | HOOPA 11013174 | 17.9584 | 2544.236 | 47.2681 | 80 | 2400 MILE | 1. <= 10% | 2.7308 | 0.027879 | 0.14824 | 14.7663 | 0.28524
SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 18.6014 | 589.0944 | 47.1288 | 81 | 2400 MILE | 1. <= 10% | 13.6967 | 0 | 0.19885 | 4.5442 | 0.16158
COTTONWOOD 1101 | COTTONWOOD 11011610 | 36.9835 | 1026.8085 | 47.0755 | 82 | 2400 MILE | 1. <= 10% | 33.0538 | 0.28654 | 0.18438 | 4.4081 | 0
DESCHUTES 1104 | DESCHUTES 1104circuit_breaker | 12.8816 | 274.7076 | 47.0625 | 83 | 2400 MILE | 1. <= 10% | 11.202 | 0 | 0 | 0.79348 | 0.88617
NARROWS 2101 | NARROWS 21011202 | 45.5236 | 1236.9595 | 46.9198 | 84 | 2400 MILE | 1. <= 10% | 37.0378 | 0.060713 | 0.21285 | 8.6216 | 0
GARBERVILLE 1102 | GARBERVILLE 11024744 | 17.0549 | 1491.0883 | 46.6949 | 85 | 2400 MILE | 1. <= 10% | 13.9798 | 0 | 0 | 2.829 | 0.24606
ZACA 1102 | ZACA 1102Y54 | 31.6285 | 421.3499 | 46.1305 | 86 | 2400 MILE | 1. <= 10% | 30.385 | 0.02492 | 0 | 1.628 | 0
CALISTOGA 1101 | CALISTOGA 1101734 | 6.5844 | 851.5175 | 45.8739 | 87 | 2400 MILE | 1. <= 10% | 1.5384 | 0 | 0.18791 | 4.5206 | 0.33751
DESCHUTES 1101 | DESCHUTES 11011380 | 17.2778 | 492.8387 | 45.457 | 88 | 2400 MILE | 1. <= 10% | 13.4414 | 0 | 0 | 2.8474 | 0.98904
MARIPOSA 2102 | MARIPOSA 21029590 | 35.7947 | 1638.6727 | 45.0319 | 89 | 2400 MILE | 1. <= 10% | 29.8374 | 0.092557 | 0.20373 | 4.8547 | 0.80634
FRUITLAND 1142 | FRUITLAND 114263170 | 11.7598 | 2045.7272 | 44.7728 | 90 | 2400 MILE | 1. <= 10% | 1.74 | 0 | 0.36455 | 9.6013 | 0.053924
WISE 1102 | WISE 11022054 | 13.3888 | 354.5124 | 44.5387 | 91 | 2400 MILE | 1. <= 10% | 10.3447 | 0.25224 | 0 | 1.3441 | 1.4478
SHINGLE SPRINGS 2110 | SHINGLE SPRINGS 21107742 | 45.1951 | 2517.8085 | 43.7888 | 92 | 2400 MILE | 1. <= 10% | 36.8173 | 0.033097 | 0.21397 | 7.9773 | 0.15338
SAND CREEK 1103 | SAND CREEK 110345190 | 36.3677 | 653.3651 | 43.6523 | 93 | 2400 MILE | 1. <= 10% | 35.1568 | 0.12203 | 0 | 1.1468 | 0
DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 110519910 | 19.3129 | 547.1967 | 43.153 | 94 | 2400 MILE | 1. <= 10% | 16.9441 | 0.45564 | 0 | 3.4716 | 0
ELK CREEK 1101 | ELK CREEK 11012106 | 13.2513 | 418.9678 | 42.9776 | 95 | 2400 MILE | 1. <= 10% | 5.5149 | 7.7985 | 0 | 0 | 0
DOBBINS 1101 | DOBBINS 11011264 | 35.6102 | 3459.0259 | 42.8508 | 96 | 2400 MILE | 1. <= 10% | 16.9026 | 0.33296 | 0.39593 | 14.377 | 3.6016
GIRVAN 1101 | GIRVAN 11011330 | 30.568 | 1827.8054 | 42.5749 | 97 | 1800 MILE | 1. <= 10% | 18.8088 | 1.5861 | 0.39904 | 6.3222 | 3.4519
VOLTA 1101 | VOLTA 110180454 | 32.1124 | 2042.3945 | 42.5679 | 98 | 2400 MILE | 1. <= 10% | 21.917 | 0.063039 | 0 | 8.8121 | 1.3203
TIVY VALLEY 1107 | TIVY VALLEY 1107R1817 | 14.5887 | 813.3371 | 42.3833 | 99 | 2400 MILE | 1. <= 10% | 12.9863 | 0.069968 | 0.067201 | 0.65128 | 0.81397
AUBERRY 1102 | AUBERRY 1102R2850 | 26.3385 | 404.9973 | 42.1507 | 100 | 2400 MILE | 1. <= 10% | 23.5909 | 0.23257 | 0 | 2.2572 | 0.2578
BELL 1107 | BELL 110750172 | 5.4542 | 377.1206 | 41.2852 | 103 | 2400 MILE | 1. <= 10% | 4.7946 | 0 | 0 | 0.54588 | 0.11374
EL DORADO PH 2101 | EL DORADO PH 210126000 | 33.1648 | 7802.1805 | 39.29 | 116 | 2400 MILE | 1. <= 10% | 0.14569 | 0 | 1.2926 | 19.4894 | 12.2371
SILVERADO 2104 | SILVERADO 210478268 | 6.1977 | 692.1399 | 18.9223 | 243 | 2400 MILE | 1. <= 10% | 3.4253 | 0.17086 | 0.22233 | 2.2655 | 0.1137
GIRVAN 1102 | GIRVAN 11021028 | 18.438 | 842.8495 | 13.4089 | 317 | 2400 MILE | 1. <= 10% | 9.78 | 0 | 0.60953 | 4.9251 | 3.1234
COLUMBIA HILL 1101 | COLUMBIA HILL 1101circuit_breaker | 38.7649 | 3782.5319 | 8.3581 | 467 | 2400 MILE | 2. >10 - 20% | 5.5251 | 0.17628 | 0.04606 | 28.9932 | 4.0242
GEYSERVILLE 1101 | GEYSERVILLE 110137454 | 6.3661 | 374.0536 | 8.3089 | 470 | 2400 MILE | 2. >10 - 20% | 4.6202 | 0 | 5.266e-05 | 1.6202 | 0.12566
BRUNSWICK 1103 | BRUNSWICK 110350070 | 26.7904 | 4858.7405 | 6.6564 | 531 | 2400 MILE | 2. >10 - 20% | 2.1844 | 0.0023144 | 0.0073351 | 23.3191 | 1.2774
SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 1107V60 | 15.5202 | 654.6037 | 4.4912 | 650 | 2400 MILE | 3. >20 - 30% | 13.9636 | 0.0099527 | 0 | 0.77448 | 0.77216
WISHON 1101 | WISHON 1101circuit_breaker | 5.3091 | 317 | 2.4746 | 827 | 2400 MILE | 3. >20 - 30% | 3.4651 | 0 | 0 | 1.6223 | 0.22166
Total |  | 2645.7182 | [5 empty] | 1895.0887 | 58.8081 | 23.3052 | 580.4779 | 112.8754
Note: “As part of EVM’s process, a circuit segment categorized as completed (work verified), may revert to an in-progress status if a new vegetation point (tree) is associated with a circuit segment after the work verification was completed. If this were to occur, miles associated with this circuit segment will not be recognized as complete until work verification has been re-performed. This condition could cause progress which was recognized in one quarter to not be recognized in a subsequent quarter.”